## Team
Initials | First | Last | Email | GitHub Username
pr | Paveethra | Raman Krishnakumar | pramankr@stevens.edu | PaveethraRaman
dk | Dheeraj Reddy | Kadiveti | dkadivet@stevens.edu | DheerajReddyKadiveti
sb | Siddharth | Bhojanapalli | sbhojana@stevens.edu | sid9703
nb | Laxmi Narasimha | Bachu | lbachu@stevens.edu | Laxminarasimha4117
|  |  |  | GitHub Repository: | https://github.com/PaveethraRaman/CS555WS_Team6_Fall-2022

## Backlog
Sprint | Story ID | Story Name | Owner | Status
1 | US01 | Previous dates | PR | Not Started
1 | US02 | Unique IDs | PR | Not Started
1 | US03 | List of married individuals | DK | Not Started
1 | US04 | List of unmarried individuals | DK | Not Started
1 | US05 | Remarried individuals | SB | Not Started
1 | US06 | Widowed indiduals | SB | Not Started
1 | US07 | Family last names | NB | Not Started
1 | US08 | No marriage between siblings | NB | Not Started
| US09 | Half siblings through remarriage

## Burndown README
The goal of the burndown chart is to help the agile team and customer to understand how the developers are doing
to deliver the product. Burndown charts can be done daily, weekly, at the end of a sprint, or at whatever time interval makes sense.
We'll update our burndown chart for the GEDCOM project at the end of each sprint.
At the end of each sprint, you should update the number of remaining stories, the LOC written to implement the user stories
implemented in this sprint, and the minutes needed to write those lines of code.
Here's a sample burndown chart for a team of three:
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2022-09-26 | 32 |  | 0
Sprint 1 | 2022-10-03 | 24 | 6 | 250 | 120 | 125
Sprint 2 | 2022-10-17 | 16 | 6 | 480 | 135 | 102.2
Sprint 3 | 2022-10-31 | 8 | 6 | 740 | 160 | 97.5
Sprint 4 | 2022-11-28 | 0 | 6 | 1100 | 145 | 149
= #team members
* 4 sprints*
2 stories per sprint
Velocity of completing user stories(calculated)
Total LOC
How long to implement the user stories in this sprint
Lines of code per hour is calculated by Excel

## Burndown
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2022-09-26 | 32
1 | 2022-10-03 | 24
2 | 2022-10-17 | 16
3 | 2022-10-31 | 8
4 | 2022-11-28 | 0

## Sprint 1
Story ID | Stroy Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Previous dates | PR | Not Started | 30 | 30
US02 | Unique IDs | PR | Not Started | 20 | 30
US03 | List of married individuals | DK | Not Started | 20 | 30
US04 | List of unmarried individuals | DK | Not Started | 20 | 30
US05 | Remarried individuals | SB | Not Started | 25 | 30
US06 | Widowed indiduals | SB | Not Started | 25 | 30
US07 | Family last names | NB | Not Started | 25 | 30
US08 | No marriage between siblings | NB | Not Started | 30 | 45
Review Results
Keep doing
Avoid :

## Sprint 2
Story ID | Stroy Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint 3
Story ID | Stroy Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint4
Story ID | Stroy Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Stories
Story ID | Story Name | Stroy Description
US01 | Previous dates | Previous events ( birth , death ,marriage) before the current date
US02 | Unique IDs | All individual IDs should be unique and all family IDs should be unique
US03 | List of married individuals | List of all the individuals in the family who are married.
US04 | List of unmarried individuals | List of all the individuals in the family who are not married.
US05 | Remarried individuals | List of all the individuals in the family who are remarried after divorce or being widowed
US06 | Widowed indiduals | List of all the individuals in the family who are widowed
US07 | Family last names | Last names of every family
US08 | No marriage between siblings | Siblings from the same family should not marry one another